## Schedule
|  | Start Date: | 2022-12-30 | (Format: dd-mmm e.g. '8-Aug')
|  | Jobs Start Time: | 8:30 | (Format: hh:mm e.g. '15:02')
|  | Buffer Time: | 10 | (minutes)
|  |  | Process Start Times |  |  |  | Processing Complete |  |  |  | Post-Processing Complete
Job | StartDate | SKU | P1 | P2 | P3 | P4 | P1 | P2 | P3 | P4 | P1 | P2 | P3 | P4
1 | 2022-12-30 08:30 | a | 44925.3542 | 44925.6245 | 44925.7894 | 44925.8537 | 44925.6245 | 44925.7894 | 44925.8537 | 44925.9617 | 44925.6278 | 44925.7948 | 44925.8553 | 44925.9696
2 | 2022-12-30 15:14 | a | 44925.6347 | 44925.8017 | 44925.8622 | 44925.9766 | 44925.905 | 44925.9667 | 44925.9265 | 44926.0846 | 44925.9084 | 44925.972 | 44925.928 | 44926.0925
3 | 2022-12-30 21:53 | c | 44925.912 | 44925.979 | 44925.9859 | 44926.0995 | 44926.0322 | 44926.0103 | 44926.0124 | 44926.124 | 44926.038 | 44926.0205 | 44926.0137 | 44926.1386
4 | 2022-12-31 00:56 | d | 44926.0391 | 44926.0461 | 44926.053 | 44926.1455 | 44926.3434 | 44926.3283 | 44926.1025 | 44926.1729 | 44926.356 | 44926.3345 | 44926.1097 | 44926.1757
5 | 2022-12-31 08:24 | b | 44926.3503 | 44926.3573 | 44926.3642 | 44926.3712 | 44926.3639 | 44926.4713 | 44926.524 | 44926.5695 | 44926.3709 | 44926.4843 | 44926.5292 | 44926.5849
6 | 2022-12-31 08:54 | b | 44926.3708 | 44926.4913 | 44926.5362 | 44926.5919 | 44926.3844 | 44926.6054 | 44926.696 | 44926.7903 | 44926.3914 | 44926.6184 | 44926.7012 | 44926.8057
7 | 2022-12-31 09:23 | a | 44926.3913 | 44926.6253 | 44926.7081 | 44926.8126 | 44926.6616 | 44926.7903 | 44926.7724 | 44926.9207 | 44926.6649 | 44926.7956 | 44926.774 | 44926.9286
8 | 2022-12-31 16:03 | c | 44926.6685 | 44926.8026 | 44926.8095 | 44926.9355 | 44926.7887 | 44926.8339 | 44926.836 | 44926.9601 | 44926.7946 | 44926.8441 | 44926.8373 | 44926.9746
9 | 2022-12-31 19:06 | c | 44926.7957 | 44926.8511 | 44926.858 | 44926.9816 | 44926.9159 | 44926.8824 | 44926.8845 | 44927.0061 | 44926.9217 | 44926.8926 | 44926.8858 | 44927.0207
10 | 2022-12-31 22:09 | b | 44926.9228 | 44926.9297 | 44926.9367 | 44927.0276 | 44926.9363 | 44927.0438 | 44927.0965 | 44927.226 | 44926.9434 | 44927.0568 | 44927.1017 | 44927.2414
11 | 2022-12-31 22:38 | a | 44926.9433 | 44927.0638 | 44927.1087 | 44927.2484 | 44927.2136 | 44927.2287 | 44927.1729 | 44927.3564 | 44927.2169 | 44927.2341 | 44927.1745 | 44927.3643
12 | 2023-01-01 05:18 | d | 44927.2205 | 44927.241 | 44927.248 | 44927.3713 | 44927.5248 | 44927.5232 | 44927.2974 | 44927.3986 | 44927.5375 | 44927.5295 | 44927.3046 | 44927.4014
13 | 2023-01-01 12:46 | b | 44927.5317 | 44927.5387 | 44927.5456 | 44927.5526 | 44927.5453 | 44927.6527 | 44927.7054 | 44927.7509 | 44927.5523 | 44927.6658 | 44927.7106 | 44927.7664
14 | 2023-01-01 13:15 | d | 44927.5522 | 44927.6727 | 44927.7176 | 44927.7733 | 44927.8565 | 44927.9549 | 44927.7671 | 44927.8007 | 44927.8692 | 44927.9612 | 44927.7742 | 44927.8035
15 | 2023-01-01 20:43 | b | 44927.8634 | 44927.9681 | 44927.9751 | 44927.982 | 44927.877 | 44928.0822 | 44928.1349 | 44928.1804 | 44927.884 | 44928.0952 | 44928.1401 | 44928.1958
16 | 2023-01-01 21:13 | c | 44927.8839 | 44928.1022 | 44928.147 | 44928.2028 | 44928.0041 | 44928.1335 | 44928.1736 | 44928.2273 | 44928.01 | 44928.1437 | 44928.1749 | 44928.2419
17 | 2023-01-02 00:16 | b | 44928.0111 | 44928.1506 | 44928.1818 | 44928.2488 | 44928.0246 | 44928.2647 | 44928.3416 | 44928.4472 | 44928.0316 | 44928.2777 | 44928.3468 | 44928.4626
18 | 2023-01-02 00:45 | c | 44928.0315 | 44928.2847 | 44928.3538 | 44928.4696 | 44928.1517 | 44928.316 | 44928.3803 | 44928.4941 | 44928.1576 | 44928.3262 | 44928.3816 | 44928.5087
19 | 2023-01-02 03:48 | c | 44928.1587 | 44928.3332 | 44928.3885 | 44928.5156 | 44928.2789 | 44928.3645 | 44928.4151 | 44928.5402 | 44928.2847 | 44928.3747 | 44928.4164 | 44928.5548
20 | 2023-01-02 06:52 | a | 44928.2858 | 44928.3817 | 44928.4233 | 44928.5617 | 44928.5561 | 44928.5466 | 44928.4876 | 44928.6697 | 44928.5594 | 44928.552 | 44928.4891 | 44928.6776
21 | 2023-01-02 13:31 | c | 44928.563 | 44928.57 | 44928.5769 | 44928.6846 | 44928.6832 | 44928.6013 | 44928.6035 | 44928.7091 | 44928.6891 | 44928.6115 | 44928.6047 | 44928.7237
22 | 2023-01-02 16:34 | d | 44928.6902 | 44928.6971 | 44928.7041 | 44928.7306 | 44928.9944 | 44928.9793 | 44928.7535 | 44928.758 | 44929.0071 | 44928.9856 | 44928.7607 | 44928.7608
23 | 2023-01-03 00:02 | b | 44929.0014 | 44929.0083 | 44929.0153 | 44929.0222 | 44929.0149 | 44929.1224 | 44929.1751 | 44929.2206 | 44929.022 | 44929.1354 | 44929.1803 | 44929.236
24 | 2023-01-03 00:31 | d | 44929.0219 | 44929.1423 | 44929.1872 | 44929.2429 | 44929.3261 | 44929.4246 | 44929.2367 | 44929.2703 | 44929.3388 | 44929.4308 | 44929.2439 | 44929.2731
25 | 2023-01-03 08:00 | a | 44929.3331 | 44929.4378 | 44929.4447 | 44929.4517 | 44929.6034 | 44929.6027 | 44929.509 | 44929.5597 | 44929.6067 | 44929.6081 | 44929.5106 | 44929.5676
26 | 2023-01-03 14:39 | c | 44929.6103 | 44929.6173 | 44929.6242 | 44929.6311 | 44929.7305 | 44929.6486 | 44929.6507 | 44929.6557 | 44929.7364 | 44929.6588 | 44929.652 | 44929.6703
27 | 2023-01-03 17:42 | c | 44929.7374 | 44929.7444 | 44929.7513 | 44929.7583 | 44929.8576 | 44929.7757 | 44929.7779 | 44929.7828 | 44929.8635 | 44929.7859 | 44929.7791 | 44929.7974
28 | 2023-01-03 20:45 | a | 44929.8646 | 44929.8715 | 44929.8785 | 44929.8854 | 44930.1349 | 44930.0365 | 44929.9427 | 44929.9934 | 44930.1382 | 44930.0418 | 44929.9443 | 44930.0013
29 | 2023-01-04 03:24 | c | 44930.1418 | 44930.1487 | 44930.1557 | 44930.1626 | 44930.262 | 44930.1801 | 44930.1822 | 44930.1872 | 44930.2678 | 44930.1903 | 44930.1835 | 44930.2018
30 | 2023-01-04 06:27 | d | 44930.2689 | 44930.2759 | 44930.2828 | 44930.2898 | 44930.5732 | 44930.5581 | 44930.3323 | 44930.3171 | 44930.5858 | 44930.5644 | 44930.3395 | 44930.3199
31 | 2023-01-04 13:55 | c | 44930.5801 | 44930.5871 | 44930.594 | 44930.601 | 44930.7003 | 44930.6184 | 44930.6206 | 44930.6255 | 44930.7062 | 44930.6286 | 44930.6218 | 44930.6401
32 | 2023-01-04 16:58 | c | 44930.7073 | 44930.7142 | 44930.7211 | 44930.7281 | 44930.8274 | 44930.7455 | 44930.7477 | 44930.7526 | 44930.8333 | 44930.7557 | 44930.749 | 44930.7672
33 | 2023-01-04 20:02 | d | 44930.8344 | 44930.8413 | 44930.8483 | 44930.8552 | 44931.1386 | 44931.1236 | 44930.8977 | 44930.8826 | 44931.1513 | 44931.1298 | 44930.9049 | 44930.8854
34 | 2023-01-05 03:30 | b | 44931.1456 | 44931.1525 | 44931.1595 | 44931.1664 | 44931.1591 | 44931.2666 | 44931.3193 | 44931.3648 | 44931.1662 | 44931.2796 | 44931.3245 | 44931.3802
35 | 2023-01-05 03:59 | b | 44931.1661 | 44931.2866 | 44931.3314 | 44931.3872 | 44931.1796 | 44931.4006 | 44931.4912 | 44931.5855 | 44931.1867 | 44931.4136 | 44931.4965 | 44931.601
36 | 2023-01-05 04:29 | b | 44931.1866 | 44931.4206 | 44931.5034 | 44931.6079 | 44931.2001 | 44931.5347 | 44931.6632 | 44931.8063 | 44931.2072 | 44931.5477 | 44931.6684 | 44931.8217
37 | 2023-01-05 04:58 | d | 44931.2071 | 44931.5546 | 44931.6754 | 44931.8286 | 44931.5113 | 44931.8368 | 44931.7248 | 44931.856 | 44931.524 | 44931.8431 | 44931.732 | 44931.8588
38 | 2023-01-05 12:26 | b | 44931.5183 | 44931.85 | 44931.857 | 44931.8658 | 44931.5318 | 44931.9641 | 44932.0168 | 44932.0641 | 44931.5389 | 44931.9771 | 44932.022 | 44932.0796
39 | 2023-01-05 12:56 | a | 44931.5388 | 44931.9841 | 44932.029 | 44932.0865 | 44931.8091 | 44932.149 | 44932.0932 | 44932.1945 | 44931.8124 | 44932.1544 | 44932.0948 | 44932.2024
40 | 2023-01-05 19:35 | c | 44931.816 | 44932.1613 | 44932.1683 | 44932.2094 | 44931.9362 | 44932.1926 | 44932.1948 | 44932.2339 | 44931.9421 | 44932.2029 | 44932.1961 | 44932.2485
41 | 2023-01-05 22:38 | c | 44931.9431 | 44932.2098 | 44932.2167 | 44932.2554 | 44932.0633 | 44932.2411 | 44932.2433 | 44932.28 | 44932.0692 | 44932.2513 | 44932.2446 | 44932.2946
42 | 2023-01-06 01:41 | a | 44932.0703 | 44932.2583 | 44932.2652 | 44932.3015 | 44932.3406 | 44932.4232 | 44932.3295 | 44932.4095 | 44932.3439 | 44932.4286 | 44932.3311 | 44932.4175
43 | 2023-01-06 08:20 | a | 44932.3475 | 44932.4355 | 44932.4425 | 44932.4494 | 44932.6178 | 44932.6005 | 44932.5068 | 44932.5575 | 44932.6211 | 44932.6058 | 44932.5083 | 44932.5654
44 | 2023-01-06 15:00 | c | 44932.6247 | 44932.6317 | 44932.6386 | 44932.6456 | 44932.7449 | 44932.663 | 44932.6652 | 44932.6701 | 44932.7508 | 44932.6732 | 44932.6664 | 44932.6847
45 | 2023-01-06 18:03 | c | 44932.7519 | 44932.7588 | 44932.7657 | 44932.7727 | 44932.872 | 44932.7901 | 44932.7923 | 44932.7973 | 44932.8779 | 44932.8004 | 44932.7936 | 44932.8118
46 | 2023-01-06 21:06 | a | 44932.879 | 44932.8859 | 44932.8929 | 44932.8998 | 44933.1493 | 44933.0509 | 44932.9572 | 44933.0078 | 44933.1526 | 44933.0562 | 44932.9587 | 44933.0158
47 | 2023-01-07 03:45 | d | 44933.1562 | 44933.1632 | 44933.1701 | 44933.1771 | 44933.4605 | 44933.4454 | 44933.2196 | 44933.2044 | 44933.4731 | 44933.4517 | 44933.2268 | 44933.2072
48 | 2023-01-07 11:13 | c | 44933.4674 | 44933.4744 | 44933.4813 | 44933.4883 | 44933.5876 | 44933.5057 | 44933.5079 | 44933.5128 | 44933.5935 | 44933.5159 | 44933.5091 | 44933.5274
49 | 2023-01-07 14:16 | b | 44933.5946 | 44933.6015 | 44933.6084 | 44933.6154 | 44933.6081 | 44933.7156 | 44933.7682 | 44933.8138 | 44933.6151 | 44933.7286 | 44933.7735 | 44933.8292
50 | 2023-01-07 14:46 | b | 44933.6151 | 44933.7355 | 44933.7804 | 44933.8361 | 44933.6286 | 44933.8496 | 44933.9402 | 44934.0345 | 44933.6356 | 44933.8626 | 44933.9454 | 44934.0499
51 | 2023-01-07 15:15 | b | 44933.6355 | 44933.8696 | 44933.9524 | 44934.0569 | 44933.6491 | 44933.9836 | 44934.1122 | 44934.2552 | 44933.6561 | 44933.9966 | 44934.1174 | 44934.2707
52 | 2023-01-07 15:45 | c | 44933.656 | 44934.0036 | 44934.1243 | 44934.2776 | 44933.7762 | 44934.0349 | 44934.1509 | 44934.3022 | 44933.7821 | 44934.0451 | 44934.1522 | 44934.3167
53 | 2023-01-07 18:48 | b | 44933.7832 | 44934.0521 | 44934.1591 | 44934.3237 | 44933.7967 | 44934.1661 | 44934.3189 | 44934.5221 | 44933.8037 | 44934.1791 | 44934.3241 | 44934.5375
54 | 2023-01-07 19:17 | d | 44933.8037 | 44934.1861 | 44934.3311 | 44934.5444 | 44934.1079 | 44934.4683 | 44934.3805 | 44934.5718 | 44934.1206 | 44934.4746 | 44934.3877 | 44934.5746
55 | 2023-01-08 02:45 | a | 44934.1149 | 44934.4815 | 44934.4885 | 44934.5815 | 44934.3852 | 44934.6465 | 44934.5528 | 44934.6896 | 44934.3885 | 44934.6518 | 44934.5543 | 44934.6975
56 | 2023-01-08 09:25 | b | 44934.3921 | 44934.6588 | 44934.6657 | 44934.7044 | 44934.4057 | 44934.7728 | 44934.8255 | 44934.9028 | 44934.4127 | 44934.7858 | 44934.8307 | 44934.9182
57 | 2023-01-08 09:54 | b | 44934.4126 | 44934.7928 | 44934.8377 | 44934.9252 | 44934.4261 | 44934.9069 | 44934.9975 | 44935.1235 | 44934.4332 | 44934.9199 | 44935.0027 | 44935.1389
58 | 2023-01-08 10:24 | c | 44934.4331 | 44934.9268 | 44935.0096 | 44935.1459 | 44934.5533 | 44934.9581 | 44935.0362 | 44935.1705 | 44934.5591 | 44934.9684 | 44935.0375 | 44935.185
59 | 2023-01-08 13:27 | b | 44934.5602 | 44934.9753 | 44935.0444 | 44935.192 | 44934.5738 | 44935.0894 | 44935.2042 | 44935.3903 | 44934.5808 | 44935.1024 | 44935.2094 | 44935.4058
60 | 2023-01-08 13:56 | c | 44934.5807 | 44935.1093 | 44935.2164 | 44935.4127 | 44934.7009 | 44935.1406 | 44935.2429 | 44935.4373 | 44934.7068 | 44935.1509 | 44935.2442 | 44935.4518
61 | 2023-01-08 16:59 | c | 44934.7078 | 44935.1578 | 44935.2511 | 44935.4588 | 44934.828 | 44935.1891 | 44935.2777 | 44935.4833 | 44934.8339 | 44935.1994 | 44935.279 | 44935.4979
62 | 2023-01-08 20:02 | d | 44934.835 | 44935.2063 | 44935.2859 | 44935.5048 | 44935.1392 | 44935.4885 | 44935.3354 | 44935.5322 | 44935.1519 | 44935.4948 | 44935.3426 | 44935.535
63 | 2023-01-09 03:30 | b | 44935.1462 | 44935.5017 | 44935.5087 | 44935.5419 | 44935.1597 | 44935.6158 | 44935.6685 | 44935.7403 | 44935.1668 | 44935.6288 | 44935.6737 | 44935.7557
64 | 2023-01-09 04:00 | a | 44935.1667 | 44935.6358 | 44935.6807 | 44935.7627 | 44935.437 | 44935.8007 | 44935.7449 | 44935.8707 | 44935.4403 | 44935.8061 | 44935.7465 | 44935.8786
65 | 2023-01-09 10:39 | c | 44935.4439 | 44935.813 | 44935.82 | 44935.8856 | 44935.5641 | 44935.8443 | 44935.8465 | 44935.9101 | 44935.5699 | 44935.8546 | 44935.8478 | 44935.9247
66 | 2023-01-09 13:42 | c | 44935.571 | 44935.8615 | 44935.8684 | 44935.9316 | 44935.6912 | 44935.8928 | 44935.895 | 44935.9562 | 44935.6971 | 44935.903 | 44935.8963 | 44935.9708
67 | 2023-01-09 16:45 | d | 44935.6982 | 44935.91 | 44935.9169 | 44935.9777 | 44936.0024 | 44936.1922 | 44935.9664 | 44936.0051 | 44936.0151 | 44936.1985 | 44935.9736 | 44936.0079
68 | 2023-01-10 00:13 | d | 44936.0094 | 44936.2054 | 44936.2124 | 44936.2193 | 44936.3136 | 44936.4876 | 44936.2618 | 44936.2467 | 44936.3263 | 44936.4939 | 44936.269 | 44936.2495
69 | 2023-01-10 07:42 | b | 44936.3206 | 44936.5009 | 44936.5078 | 44936.5147 | 44936.3341 | 44936.6149 | 44936.6676 | 44936.7131 | 44936.3411 | 44936.6279 | 44936.6728 | 44936.7285
70 | 2023-01-10 08:11 | b | 44936.3411 | 44936.6349 | 44936.6798 | 44936.7355 | 44936.3546 | 44936.7489 | 44936.8396 | 44936.9339 | 44936.3616 | 44936.762 | 44936.8448 | 44936.9493
71 | 2023-01-10 08:41 | b | 44936.3616 | 44936.7689 | 44936.8517 | 44936.9562 | 44936.3751 | 44936.883 | 44937.0115 | 44937.1546 | 44936.3821 | 44936.896 | 44937.0168 | 44937.17
72 | 2023-01-10 09:10 | b | 44936.3821 | 44936.9029 | 44937.0237 | 44937.177 | 44936.3956 | 44937.017 | 44937.1835 | 44937.3753 | 44936.4026 | 44937.03 | 44937.1887 | 44937.3908
73 | 2023-01-10 09:40 | d | 44936.4025 | 44937.037 | 44937.1957 | 44937.3977 | 44936.7068 | 44937.3192 | 44937.2451 | 44937.4251 | 44936.7195 | 44937.3254 | 44937.2523 | 44937.4279
74 | 2023-01-10 17:08 | b | 44936.7138 | 44937.3324 | 44937.3393 | 44937.4348 | 44936.7273 | 44937.4465 | 44937.4991 | 44937.6332 | 44936.7343 | 44937.4595 | 44937.5043 | 44937.6486
75 | 2023-01-10 17:37 | c | 44936.7342 | 44937.4664 | 44937.5113 | 44937.6556 | 44936.8544 | 44937.4977 | 44937.5378 | 44937.6801 | 44936.8603 | 44937.508 | 44937.5391 | 44937.6947
76 | 2023-01-10 20:40 | d | 44936.8614 | 44937.5149 | 44937.5461 | 44937.7016 | 44937.1656 | 44937.7971 | 44937.5955 | 44937.729 | 44937.1783 | 44937.8034 | 44937.6027 | 44937.7318
77 | 2023-01-11 04:09 | d | 44937.1726 | 44937.8103 | 44937.8173 | 44937.8242 | 44937.4768 | 44938.0926 | 44937.8667 | 44937.8516 | 44937.4895 | 44938.0988 | 44937.8739 | 44937.8544
78 | 2023-01-11 11:37 | a | 44937.4838 | 44938.1058 | 44938.1127 | 44938.1196 | 44937.7541 | 44938.2707 | 44938.177 | 44938.2277 | 44937.7574 | 44938.2761 | 44938.1785 | 44938.2356
79 | 2023-01-11 18:16 | d | 44937.761 | 44938.283 | 44938.2899 | 44938.2969 | 44938.0653 | 44938.5652 | 44938.3394 | 44938.3243 | 44938.078 | 44938.5715 | 44938.3466 | 44938.3271
80 | 2023-01-12 01:44 | b | 44938.0722 | 44938.5784 | 44938.5854 | 44938.5923 | 44938.0858 | 44938.6925 | 44938.7452 | 44938.7907 | 44938.0928 | 44938.7055 | 44938.7504 | 44938.8061
81 | 2023-01-12 02:14 | d | 44938.0927 | 44938.7125 | 44938.7573 | 44938.8131 | 44938.397 | 44938.9947 | 44938.8068 | 44938.8404 | 44938.4097 | 44939.0009 | 44938.814 | 44938.8432
82 | 2023-01-12 09:42 | b | 44938.4039 | 44939.0079 | 44939.0148 | 44939.0218 | 44938.4175 | 44939.122 | 44939.1746 | 44939.2202 | 44938.4245 | 44939.135 | 44939.1799 | 44939.2356
83 | 2023-01-12 10:11 | b | 44938.4244 | 44939.1419 | 44939.1868 | 44939.2425 | 44938.438 | 44939.256 | 44939.3466 | 44939.4409 | 44938.445 | 44939.269 | 44939.3518 | 44939.4563
84 | 2023-01-12 10:41 | a | 44938.4449 | 44939.2759 | 44939.3588 | 44939.4633 | 44938.7152 | 44939.4409 | 44939.4231 | 44939.5713 | 44938.7186 | 44939.4462 | 44939.4246 | 44939.5792
85 | 2023-01-12 17:20 | a | 44938.7222 | 44939.4532 | 44939.4601 | 44939.5861 | 44938.9925 | 44939.6181 | 44939.5244 | 44939.6942 | 44938.9958 | 44939.6235 | 44939.526 | 44939.7021
86 | 2023-01-12 23:59 | c | 44938.9994 | 44939.6304 | 44939.6374 | 44939.709 | 44939.1196 | 44939.6617 | 44939.6639 | 44939.7336 | 44939.1254 | 44939.672 | 44939.6652 | 44939.7481
87 | 2023-01-13 03:02 | a | 44939.1265 | 44939.6789 | 44939.6859 | 44939.7551 | 44939.3968 | 44939.8439 | 44939.7502 | 44939.8631 | 44939.4002 | 44939.8492 | 44939.7517 | 44939.871
88 | 2023-01-13 09:41 | a | 44939.4038 | 44939.8562 | 44939.8631 | 44939.878 | 44939.674 | 44940.0211 | 44939.9274 | 44939.986 | 44939.6774 | 44940.0265 | 44939.9289 | 44939.9939
89 | 2023-01-13 16:21 | d | 44939.681 | 44940.0334 | 44940.0404 | 44940.0473 | 44939.9853 | 44940.3156 | 44940.0898 | 44940.0747 | 44939.9979 | 44940.3219 | 44940.097 | 44940.0775
90 | 2023-01-13 23:49 | c | 44939.9922 | 44940.3288 | 44940.3358 | 44940.3427 | 44940.1124 | 44940.3602 | 44940.3623 | 44940.3673 | 44940.1182 | 44940.3704 | 44940.3636 | 44940.3819
91 | 2023-01-14 02:52 | c | 44940.1193 | 44940.3773 | 44940.3843 | 44940.3912 | 44940.2395 | 44940.4086 | 44940.4108 | 44940.4158 | 44940.2454 | 44940.4189 | 44940.4121 | 44940.4303
92 | 2023-01-14 05:55 | d | 44940.2465 | 44940.4258 | 44940.4328 | 44940.4397 | 44940.5507 | 44940.7081 | 44940.4822 | 44940.4671 | 44940.5634 | 44940.7143 | 44940.4894 | 44940.4699
93 | 2023-01-14 13:23 | a | 44940.5577 | 44940.7213 | 44940.7282 | 44940.7351 | 44940.828 | 44940.8862 | 44940.7925 | 44940.8432 | 44940.8313 | 44940.8916 | 44940.794 | 44940.8511
94 | 2023-01-14 20:02 | d | 44940.8349 | 44940.8985 | 44940.9054 | 44940.9124 | 44941.1392 | 44941.1807 | 44940.9549 | 44940.9398 | 44941.1518 | 44941.187 | 44940.9621 | 44940.9426
95 | 2023-01-15 03:30 | c | 44941.1461 | 44941.1939 | 44941.2009 | 44941.2078 | 44941.2663 | 44941.2252 | 44941.2274 | 44941.2324 | 44941.2721 | 44941.2355 | 44941.2287 | 44941.2469
96 | 2023-01-15 06:33 | a | 44941.2732 | 44941.2802 | 44941.2871 | 44941.2941 | 44941.5435 | 44941.4451 | 44941.3514 | 44941.4021 | 44941.5469 | 44941.4505 | 44941.353 | 44941.41
97 | 2023-01-15 13:13 | b | 44941.5505 | 44941.5574 | 44941.5644 | 44941.5713 | 44941.564 | 44941.6715 | 44941.7242 | 44941.7697 | 44941.571 | 44941.6845 | 44941.7294 | 44941.7851
98 | 2023-01-15 13:42 | d | 44941.571 | 44941.6914 | 44941.7363 | 44941.792 | 44941.8752 | 44941.9737 | 44941.7858 | 44941.8194 | 44941.8879 | 44941.9799 | 44941.793 | 44941.8222
99 | 2023-01-15 21:10 | b | 44941.8822 | 44941.9869 | 44941.9938 | 44942.0008 | 44941.8957 | 44942.1009 | 44942.1536 | 44942.1991 | 44941.9027 | 44942.1139 | 44942.1588 | 44942.2146
100 | 2023-01-15 21:40 | c | 44941.9027 | 44942.1209 | 44942.1658 | 44942.2215 | 44942.0228 | 44942.1522 | 44942.1923 | 44942.2461 | 44942.0287 | 44942.1624 | 44942.1936 | 44942.2606
101 | 2023-01-16 00:43 | a | 44942.0298 | 44942.1694 | 44942.2005 | 44942.2676 | 44942.3001 | 44942.3343 | 44942.2648 | 44942.3756 | 44942.3034 | 44942.3397 | 44942.2664 | 44942.3835
102 | 2023-01-16 07:22 | c | 44942.307 | 44942.3466 | 44942.3536 | 44942.3904 | 44942.4272 | 44942.3779 | 44942.3801 | 44942.415 | 44942.4331 | 44942.3882 | 44942.3814 | 44942.4296
103 | 2023-01-16 10:25 | b | 44942.4342 | 44942.4411 | 44942.448 | 44942.455 | 44942.4477 | 44942.5552 | 44942.6078 | 44942.6534 | 44942.4547 | 44942.5682 | 44942.6131 | 44942.6688
104 | 2023-01-16 10:55 | b | 44942.4546 | 44942.5751 | 44942.62 | 44942.6757 | 44942.4682 | 44942.6892 | 44942.7798 | 44942.8741 | 44942.4752 | 44942.7022 | 44942.785 | 44942.8895
105 | 2023-01-16 11:14 | d | 44942.4682 | 44942.6961 | 44942.7867 | 44942.881 | 44942.7725 | 44942.9784 | 44942.8362 | 44942.9084 | 44942.7851 | 44942.9846 | 44942.8434 | 44942.9112
Formulas:
StartDate = [Process Start Times]
Note on C3: David D.: Time left as empty buffer between projected start time of process, and time used

## GanttChart
Start Date Override:
Start Time Override: |  | 44925.2917 | 44925.2986 | 44925.3056 | 44925.3125 | 44925.3194 | 44925.3264 | 44925.3333 | 44925.3403 | 44925.3472 | 44925.3542 | 44925.3611 | 44925.3681 | 44925.375 | 44925.3819 | 44925.3889 | 44925.3958 | 44925.4028 | 44925.4097 | 44925.4167 | 44925.4236 | 44925.4306 | 44925.4375 | 44925.4444 | 44925.4514 | 44925.4583 | 44925.4653 | 44925.4722 | 44925.4792 | 44925.4861 | 44925.4931 | 44925.5 | 44925.5069 | 44925.5139 | 44925.5208 | 44925.5278 | 44925.5347 | 44925.5417 | 44925.5486 | 44925.5556 | 44925.5625 | 44925.5694 | 44925.5764 | 44925.5833 | 44925.5903 | 44925.5972 | 44925.6042 | 44925.6111 | 44925.6181 | 44925.625 | 44925.6319 | 44925.6389 | 44925.6458 | 44925.6528 | 44925.6597 | 44925.6667 | 44925.6736 | 44925.6806 | 44925.6875 | 44925.6944 | 44925.7014 | 44925.7083 | 44925.7153 | 44925.7222 | 44925.7292 | 44925.7361 | 44925.7431 | 44925.75 | 44925.7569 | 44925.7639 | 44925.7708 | 44925.7778 | 44925.7847 | 44925.7917 | 44925.7986 | 44925.8056 | 44925.8125 | 44925.8194 | 44925.8264 | 44925.8333 | 44925.8403 | 44925.8472 | 44925.8542 | 44925.8611 | 44925.8681 | 44925.875 | 44925.8819 | 44925.8889 | 44925.8958 | 44925.9028 | 44925.9097 | 44925.9167 | 44925.9236 | 44925.9306 | 44925.9375 | 44925.9444 | 44925.9514 | 44925.9583 | 44925.9653 | 44925.9722 | 44925.9792 | 44925.9861 | 44925.9931 | 44926 | 44926.0069 | 44926.0139 | 44926.0208 | 44926.0278 | 44926.0347 | 44926.0417 | 44926.0486 | 44926.0556 | 44926.0625 | 44926.0694 | 44926.0764 | 44926.0833 | 44926.0903 | 44926.0972 | 44926.1042 | 44926.1111 | 44926.1181 | 44926.125 | 44926.1319 | 44926.1389 | 44926.1458 | 44926.1528 | 44926.1597 | 44926.1667 | 44926.1736 | 44926.1806 | 44926.1875 | 44926.1944 | 44926.2014 | 44926.2083 | 44926.2153 | 44926.2222 | 44926.2292 | 44926.2361 | 44926.2431 | 44926.25 | 44926.2569 | 44926.2639 | 44926.2708 | 44926.2778 | 44926.2847 | 44926.2917 | 44926.2986 | 44926.3056 | 44926.3125 | 44926.3194 | 44926.3264 | 44926.3333 | 44926.3403 | 44926.3472 | 44926.3542
Time Interval Override: | Date | 12/30 | [101 empty] | 12/31
| Time |  |  | - | - |  |  | 8 |  | - | - |  |  | 9 |  | - | - |  |  | 10 |  | - | - |  |  | 11 |  | - | - |  |  | 12 |  | - | - |  |  | 13 |  | - | - |  |  | 14 |  | - | - |  |  | 15 |  | - | - |  |  | 16 |  | - | - |  |  | 17 |  | - | - |  |  | 18 |  | - | - |  |  | 19 |  | - | - |  |  | 20 |  | - | - |  |  | 21 |  | - | - |  |  | 22 |  | - | - |  |  | 23 |  | - | - |  |  | 0 |  | - | - |  |  | 1 |  | - | - |  |  | 2 |  | - | - |  |  | 3 |  | - | - |  |  | 4 |  | - | - |  |  | 5 |  | - | - |  |  | 6 |  | - | - |  |  | 7 |  | - | - |  |  | 8 |  | - | -
| P1 Usr Cnt | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2
| P1 Job #('s) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 9
| P1 Clr | e | e | e | e | e | e | e | e | e | e | 1 | f | f | f | f | f | f | f | f | f | f | f | f | f | f | f | f | f | f | f | f | f | f | f | f | f | f | f | f | f | f | f | f | f | f | f | f | f | f | e | 2 | f | f | f | f | f | f | f | f | f | f | f | f | f | f | f | f | f | f | f | f | f | f | f | f | f | f | f | f | f | f | f | f | f | f | f | f | f | f | e | 3 | f | f | f | f | f | f | f | f | f | f | f | f | f | f | f | f | f | 4 | f | f | f | f | f | f | f | f | f | f | f | f | f | f | f | f | f | f | f | f | f | f | f | f | f | f | f | f | f | f | f | f | f | f | f | f | f | f | f | f | f | f | f | f | r
| P1 | . | . | . | . | . | . | . | . | . | . | 1 | , | , | , | , | , | , | , | , | , | , | , | , | , | , | , | , | , | , | , | , | , | , | , | , | , | , | , | , | , | , | , | , | , | , | , | , | , | , | . | 2 | , | , | , | , | , | , | , | , | , | , | , | , | , | , | , | , | , | , | , | , | , | , | , | , | , | , | , | , | , | , | , | , | , | , | , | , | , | , | . | 3 | , | , | , | , | , | , | , | , | , | , | , | , | , | , | , | , | , | 4 | , | , | , | , | , | , | , | , | , | , | , | , | , | , | , | , | , | , | , | , | , | , | , | , | , | , | , | , | , | , | , | , | , | , | , | , | , | , | , | , | , | , | , | , | `
| P2 Usr Cnt | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
| P2 Job #('s) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0
| P2 Clr | e | e | e | e | e | e | e | e | e | e | e | e | e | e | e | e | e | e | e | e | e | e | e | e | e | e | e | e | e | e | e | e | e | e | e | e | e | e | e | e | e | e | e | e | e | e | e | e | 1 | f | f | f | f | f | f | f | f | f | f | f | f | f | f | f | f | f | f | f | f | f | f | f | f | e | 2 | f | f | f | f | f | f | f | f | f | f | f | f | f | f | f | f | f | f | f | f | f | f | f | e | 3 | f | f | f | f | f | e | e | e | e | 4 | f | f | f | f | f | f | f | f | f | f | f | f | f | f | f | f | f | f | f | f | f | f | f | f | f | f | f | f | f | f | f | f | f | f | f | f | f | f | f | f | f | e | e | e
| P2 | . | . | . | . | . | . | . | . | . | . | . | . | . | . | . | . | . | . | . | . | . | . | . | . | . | . | . | . | . | . | . | . | . | . | . | . | . | . | . | . | . | . | . | . | . | . | . | . | 1 | , | , | , | , | , | , | , | , | , | , | , | , | , | , | , | , | , | , | , | , | , | , | , | , | . | 2 | , | , | , | , | , | , | , | , | , | , | , | , | , | , | , | , | , | , | , | , | , | , | , | . | 3 | , | , | , | , | , | . | . | . | . | 4 | , | , | , | , | , | , | , | , | , | , | , | , | , | , | , | , | , | , | , | , | , | , | , | , | , | , | , | , | , | , | , | , | , | , | , | , | , | , | , | , | , | . | . | .
| P3 Usr Cnt | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| P3 Job #('s) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| P3 Clr | e | e | e | e | e | e | e | e | e | e | e | e | e | e | e | e | e | e | e | e | e | e | e | e | e | e | e | e | e | e | e | e | e | e | e | e | e | e | e | e | e | e | e | e | e | e | e | e | e | e | e | e | e | e | e | e | e | e | e | e | e | e | e | e | e | e | e | e | e | e | e | e | 1 | f | f | f | f | f | f | f | f | f | e | 2 | f | f | f | f | f | f | f | f | e | e | e | e | e | e | e | e | 3 | f | f | f | e | e | e | e | e | e | 4 | f | f | f | f | f | f | f | e | e | e | e | e | e | e | e | e | e | e | e | e | e | e | e | e | e | e | e | e | e | e | e | e | e | e | e | e | e | e | e | e | e | e | e
| P3 | . | . | . | . | . | . | . | . | . | . | . | . | . | . | . | . | . | . | . | . | . | . | . | . | . | . | . | . | . | . | . | . | . | . | . | . | . | . | . | . | . | . | . | . | . | . | . | . | . | . | . | . | . | . | . | . | . | . | . | . | . | . | . | . | . | . | . | . | . | . | . | . | 1 | , | , | , | , | , | , | , | , | , | . | 2 | , | , | , | , | , | , | , | , | . | . | . | . | . | . | . | . | 3 | , | , | , | . | . | . | . | . | . | 4 | , | , | , | , | , | , | , | . | . | . | . | . | . | . | . | . | . | . | . | . | . | . | . | . | . | . | . | . | . | . | . | . | . | . | . | . | . | . | . | . | . | . | .
| P4 Usr Cnt | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| P3 Job #('s) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 3 | 3 | 3 | 3 | 3 | 0 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| P4 Clr | e | e | e | e | e | e | e | e | e | e | e | e | e | e | e | e | e | e | e | e | e | e | e | e | e | e | e | e | e | e | e | e | e | e | e | e | e | e | e | e | e | e | e | e | e | e | e | e | e | e | e | e | e | e | e | e | e | e | e | e | e | e | e | e | e | e | e | e | e | e | e | e | e | e | e | e | e | e | e | e | e | 1 | f | f | f | f | f | f | f | f | f | f | f | f | f | f | f | f | e | 2 | f | f | f | f | f | f | f | f | f | f | f | f | f | f | f | f | e | 3 | f | f | f | f | e | 4 | f | f | f | f | e | e | e | e | e | e | e | e | e | e | e | e | e | e | e | e | e | e | e | e | e | e | e | e | e | e
| P4 | . | . | . | . | . | . | . | . | . | . | . | . | . | . | . | . | . | . | . | . | . | . | . | . | . | . | . | . | . | . | . | . | . | . | . | . | . | . | . | . | . | . | . | . | . | . | . | . | . | . | . | . | . | . | . | . | . | . | . | . | . | . | . | . | . | . | . | . | . | . | . | . | . | . | . | . | . | . | . | . | . | 1 | , | , | , | , | , | , | , | , | , | , | , | , | , | , | , | , | . | 2 | , | , | , | , | , | , | , | , | , | , | , | , | , | , | , | , | . | 3 | , | , | , | , | . | 4 | , | , | , | , | . | . | . | . | . | . | . | . | . | . | . | . | . | . | . | . | . | . | . | . | . | . | . | . | . | .
Note on D1: David D: Manually select the start date of the Gantt chart. Use Format "MMM-DD" Example: "Nov-15"
Note on D2: David D: Manually select the start time of the Gantt Chart. Use format "HH:MM" Example: 15:30 The start time will always be the previous start of hour, 4 hours back from the entered time.
Note on E2: David De Sa: The row to the right contains the exact time of each cell. First cell contains the formula referencing override times
Note on D3: David D: Value in minutes. If blank, default=10 Recommend a # that divides evenly into an hour. Eg. 10,20,30. Hours are marked. Cells that the start of which refer to minutes 20 and 30 are marked with hyphen so that by default the hyphens straddle the half hour mark

## Process Times
SKU | Process# | Processing_Time | Post-Processing_Time
a | 1 | 0.27029 | 0.0033478
a | 2 | 0.16496 | 0.0053454
a | 3 | 0.064286 | 0.001551
a | 4 | 0.10802 | 0.0079129
b | 1 | 0.01355 | 0.0070292
b | 2 | 0.11407 | 0.013012
b | 3 | 0.1598 | 0.0052262
b | 4 | 0.19838 | 0.015419
c | 1 | 0.12018 | 0.0058605
c | 2 | 0.031314 | 0.010232
c | 3 | 0.02654 | 0.0012782
c | 4 | 0.024559 | 0.014563
d | 1 | 0.30426 | 0.012662
d | 2 | 0.28223 | 0.0062593
d | 3 | 0.049468 | 0.007193
d | 4 | 0.027371 | 0.0028034

## Visual Explanation
Each process is given a 'processing time' and a 'post-processing time'. The idea behind this is that, just being the WIP material can be passed on to the next station doesn't mean the station that's finished processing is ready ot receive another piece. There could be time required for machine changeover, tool cleaning or prep, etc.
Time: | 7am | 8am | 9am | 10am | 11am | 12pm | 1pm | 2pm | 3pm
P1 | 7am: In this time, P1 is processing job 1; 10am: Job 1 clean up; 11am: Job 2 is processed; 1pm: P2 clean up; 2pm: …
P2 | 10am: Doing Job 1; 11am: Job 1 Clean up; 12pm: --Waiting--; 1pm: Doing Job 2; 2pm: …
The sequence of operations shown above is displayed as below in the Gantt Chart method used in this workbook; 'post-processing' vs processing is not visually differentiated, colour just represents busy or not busy state
Time: | 7am | 8am | 9am | 10am | 11am | 12pm | 1pm | 2pm | 3pm
P1 | bar: 7am to 2pm
P2 | bar: 10am to 11am; 1pm to 2pm
Red colour indicates if there is a potential conflict (2 job assignments to the same time period). This can be a false flag when one job stops and the next starts inside the same time chunk. Making the time-chunks smaller will increase resolution, to the point of the process start/end being seen as expected and without falsely flagging a conflict.